# SWAG Securities WGHSIC 2026-27 Team Prep Plan

Peter · Giang · Bao · Valt · Long · Tin Tin

Built for a six-person team starting from zero on 22 August 2026.

- Sources checked 20-21 August 2026; team-size and role-structure facts re-checked 24 August 2026.

- Six is Wharton’s confirmed hard maximum team size: exceeding it disqualifies the team at any point, not just at registration. No further additions are possible, the team is now at the ceiling.

- Revision note: this pass adds Tin Tin as a sixth member, adds a dated status check ahead of Part 1, and updates Part 3 (Who Owns What) to a four-role structure with Role A held jointly by two people.

- Session 7, the teach-back pairings, and the single-points-of-failure table are all updated to match.

# Status check: 24 August 2026

External verification against Wharton’s live site on 24 August 2026 re-confirmed the Key Dates already stated in this plan: IPS due 6 November, Final Report and school documentation due 4 December, Global Finale 29–30 April 2027. An earlier draft had flagged these same facts as unverified; that flag is resolved in this plan’s favor below, not re-litigated.

## CONFIRMED – source: official Wharton Global Youth Program competition pages, checked 24 Aug 2026

- Registration: 10 Aug – 11 Sep 2026, closes 5:00 p.m. ET

- Case study release: 15 Sep 2026 via SurveyMonkey Apply

- Competition trading: 28 Sep – 4 Dec 2026

- Team roster due: 9 Oct 2026, 5:00 p.m. ET

- IPS due: 6 Nov 2026, 5:00 p.m. ET

- Final Report and school documentation due: 4 Dec 2026, 5:00 p.m. ET

- Global Finale: 29–30 Apr 2027, Philadelphia

- Team size: minimum 4, maximum 6, at every point in the competition

- Global Finalists: top 10 teams advance (2026’s 11 was a stated one-off exception, not the norm)

- Advisor may oversee up to 5 teams

- Five deliverables required: team roster, school documentation, trading notes and justification, IPS, Final Report

## CARRIED OVER

Nothing to carry forward yet in this pass. This tag is reserved for facts that roll forward unchanged from a prior version of this plan without fresh verification; it starts getting used at the 15 September case-release update.

## UNVERIFIED – wait for the 15 Sep case release, do not resolve by guessing

- Starting virtual capital (commonly cited as $500,000, not found on any official page checked)

- Allowed securities scope (whether international stocks and Treasuries are included alongside US-listed stocks/ETFs)

- Single-position cap (older cycles used 25% as an example)

- Commission structure (~$25/stock trade, ~$10/Treasury trade cited elsewhere, not on an official page)

Re-check trigger: revisit this block every time new official Wharton information lands, starting with the 15 September case release, and update it then. Do not leave it static after this edit.

# Read this first

Nobody outside the competition knows what the IPS and final report must contain yet.

- Wharton releases the case study, trading rules, deliverable instructions and evaluation criteria to registered teams via SurveyMonkey Apply on 15 September 2026

- There's no public rubric and no published winning reports. Anyone telling your team otherwise is guessing

- Block A below is built on skills that are certain regardless of the case, and Session 11 is reserved for rewriting the rest once the real instructions land

Wharton actually requires five deliverables, not three.

- The official team roster, school documentation, trading notes and justification, the IPS, and the final report

- Confirmed directly from Wharton's FAQ page (fetched 21 Aug 2026)

- Trading notes are the one that's easiest to still miss even knowing this. They're graded alongside the IPS and final report

- Every trade needs a written reason recorded the moment it's placed, not reconstructed in November from memory

Is this achievable? Yes.

- A team of six beginners can produce a competitive IPS by 6 November at 6 hours a week each

- Wharton says explicitly that portfolio growth has little to do with the outcome. This is a writing and reasoning contest with a modest finance floor, not a stock-picking contest

- Eighty-six hours per person is more than enough

- What actually threatens the team is administrative (registration, advisor follow-through) and informational (not knowing the real case until 15 September), not a lack of ability

Time budget: roughly 8 hours are held back from the 86-hour ceiling as buffer. Programmed work totals about 78 hours per person.

Every skill area below starts everyone at zero. No one skips foundations. Uniform floor coverage is the point, because any of you can get pulled up at semifinals to defend a part you didn’t personally write.

RESOURCE LIBRARY: every link, one place

Everything below is free, self-paced, and has zero connection to the competition, which is what keeps everyone clean on the no-outside-courses rule. “Verified” is the date each was last confirmed live.

## Floor knowledge links: everyone, no exceptions

| ID | Resource | Source | Time | Notes |
| --- | --- | --- | --- | --- |
| R1 | Khan Academy, “Interest and debt” | Khan Academy | ~30–45 min | Floor |
| R2 | Khan Academy, “Stocks and bonds” | Khan Academy | ~45 min | Floor |
| R3 | Wharton Global Youth video glossary | Wharton Global Youth | Lookup, ongoing | Floor |
| R4 | Wharton Rules and Roles + FAQ | Wharton Global Youth | ~30 min combined | Floor |
| R5 | Investor.gov, “Types of Orders” | SEC | 10 min | Floor |
| R6 | Investor.gov, “Characteristics of MutualFunds and ETFs” | SEC | 20 min | Floor |
| R7 | Investor.gov, “Mutual Fund and ETF Feesand Expenses” | SEC | 15 min | Floor |
| R9 | FINRA Fund Analyzer | FINRA | 30 min | Floor tool, no stable direct link confirmed |
| R10 | WInS practice environment | Wharton / StockTrak | 15–25 Sep window only | Floor |
| R11 | CFA Institute, “Elements of an IPS forIndividual Investors” (PDF) | CFA Institute | ~25 pages | Floor: asset allocation + risk sections. Role A reads in full |
| R12 | CFA Institute Asset Manager Code | CFA Institute | Short skim | Floor |

R11 is the single highest-value resource in the whole plan: the professional template for the exact document you’re graded on.

## Role A links: IPS, Client & Editorial Owner (Tin Tin + co-owner)

| ID | Resource | Source | Time | Notes |
| --- | --- | --- | --- | --- |
| R11 | CFA Institute IPS elements (PDF) | CFA Institute | ~25 pages | Full document, not just the floor extract |
| R17 | Open Yale ECON 252, L11, Behavioral Finance | Yale / Shiller | ~75 min |  |
| R18 | Open Yale ECON 252, L20, Professional Money Managers | Yale / Shiller | ~75 min | Optional, cut if short |
| R19 | MIT OCW 15.401, Sessions 2–3 (Present Value) | MIT Sloan / Lo | ~2.7 hrs | Optional, discounting already covered at floor level |
| R22 | FRED | St. Louis Fed | ~90 min to learn | Interpretation only. Role D builds the pipeline |

## Role B links: Portfolio & Risk Owner

| ID | Resource | Source | Time | Notes |
| --- | --- | --- | --- | --- |
| R13 | Open Yale ECON 252, L2, Risk andFinancial Crises | Yale / Shiller | ~75 min |  |
| R14 | Open Yale ECON 252, L4, Portfolio Diversification | Yale / Shiller | ~75 min |  |
| R15 | Open Yale ECON 252, L7, Efficient Markets | Yale / Shiller | ~75 min |  |
| R20 | MIT OCW 15.401, Sessions 13–14(Risk/Return II; Portfolio Theory I) | MIT Sloan / Lo | ~2.7 hrs |  |
| R21 | MIT OCW 15.401, Sessions 15–16(Portfolio Theory III; CAPM/APT) | MIT Sloan / Lo | ~2.7 hrs | Same course page as R20 |

## Role C links: Instruments & Trading Owner

| ID | Resource | Source | Time | Notes |
| --- | --- | --- | --- | --- |
| R8 | “Mutual Funds and ETFs: A Guide forInvestors” (PDF) | SEC | ~30 pages |  |
| R16 | Open Yale ECON 252 (2011), L9,Corporate Stocks | Yale / Shiller | ~75 min | Optional, cut if short |

## Role D links: Coding & Quantitative Modelling Owner (Peter, Giang)

| ID | Resource | Source | Time | Notes |
| --- | --- | --- | --- | --- |
| R22 | FRED | St. Louis Fed | ~90 min to learn | Build and run the pipeline. Role A writes the interpretation |
| R23 | yfinance documentation | Ran Aroussi (open source) | ~1 hr |  |
| R24 | pandas, “10 Minutes to pandas” | pandas / NumFOCUS | ~30–45 min |  |
| R25 | PyPortfolioOpt documentation | Robert Martin (MIT licence) | ~2–3 hrs | Correlation/covariance, mean-variance optimization, efficient frontier |
| R26 | fredapi (Python wrapper for FRED) | mortada (open source) | ~1 hr |  |
| R27 | FRED API key signup | St. Louis Fed | ~5 min, free | Practical step, not a study resource |

PyPortfolioOpt is purpose-built, open-source, and computes correlation/covariance matrices, mean-variance optimization, and the efficient frontier directly. It is portfolio math, not a DCF or valuation tool.

PART 1: WHAT WHARTON ACTUALLY REQUIRES

## What’s confirmed, straight from Wharton (checked 20–21 Aug 2026)

- Team structure: four to six students from the same high school, one teacher advisor, one student team leader (Peter) aged 16+ on 28 September 2026. Your team of six is now at Wharton’s confirmed maximum.

  - One shared WInS account for all six of you

  - Fall below four or exceed six at any point and the team is disqualified, not just at the start The team is at that maximum now, so this is an active constraint, not a hypothetical one.

- Registration: the advisor registers both themselves and the team. Only the advisor and team leader’s (Peter’s) name are needed at this stage. Opened 10 August, closes 11 September 5:00 p.m. ET. Student WInS accounts must exist by that same moment.

- Two platforms: SurveyMonkey Apply is the hub (case study, instructions, submissions). WInS (edu.stocktrak.com/wharton) is where you actually trade. Practice window 15–25 September, portfolios wiped 4:00

p.m. ET on the 25th.

- Five deliverables, not three: official team roster (due 9 Oct, all 6 names), school documentation, trading notes and justification, the IPS, the Comprehensive Final Report, plus meeting minimum trading activity requirements.

  - This exact five-item list is on Wharton’s FAQ page. The Rules & Roles page buckets it as four “Deliverables” plus a separate “Trading Requirements” line. Same substance, different bucketing.

- Teams may not contact the competition client. Stated directly in Rules & Roles. Violating it is grounds for disqualification.

- How you’re judged: not by portfolio performance, Wharton says WInS standings have little to do with the outcome. Judged on strategy quality, alignment with the client’s objectives, depth of research, and how clearly you can defend it live. No individual feedback given, ever.

- Semifinals: top 50 selected on IPS + final report strength, virtual. Every team member has to be part of the presentation, any of you could get a question on any section. If you make the top 50, you’ll separately need school-letterhead documentation, distinct from the general school documentation deliverable and can wait until you’re actually in that position.

- AI policy: allowed for brainstorming, never as submitted work, and anything AI-assisted must be cited.

- The rule that keeps you clean: no paid advisors, no consultants, no outside course that claims to teach this competition. Wharton says it uses investigators. Every resource in this plan is general finance or coding education with zero connection to the competition. Wharton also tells every team to operate by the CFA Institute Asset Manager Code.

## Key dates: pin this where everyone can see it

| Date | What happens | In Ho Chi Minh City |
| --- | --- | --- |
| 10 Aug 2026 | Registration opened | passed |
| 11 Sep 2026, 5:00 p.m. ET | Registration closes; all student team accounts created | 4:00 a.m. Sat 12 Sep |
| 15 Sep 2026 | SurveyMonkey Apply; case study, trading rules,deliverable instructions released | 15 Sep |
| 15 to 25 Sep 2026 | WInS practice window; practice portfolios deleted at close | ends 3:00 a.m. Sat 26 Sep |
| 28 Sep 2026 | Competition begins, first day of trading | 28 Sep |
| 9 Oct 2026 | Official team roster + team name due (all 6 names), exacttime TBD, confirm at case release | ~evening 9 Oct, treat as before |
| 6 Nov 2026, 5:00 p.m. ET | IPS due | 5:00 a.m. Sat 7 Nov |
| 4 Dec 2026, 5:00 p.m. ET | Final report due | 5:00 a.m. Sat 5 Dec |
| TBD | Semifinalists announced; virtual semifinals |  |

- Every 5:00 p.m. ET deadline lands in the small hours of Saturday your time. Treat every deadline as the evening before, local

## What’s inferred, not confirmed

- The IPS will likely follow the standard professional structure (objectives, constraints, allocation policy), built against the CFA Institute template. Expect to adjust on 15 Sep.

- Starting virtual cash around $500,000, US-listed stocks and ETFs only. Third-party sources say this, Wharton itself only says “approved securities.” Don’t lock in a strategy around a specific security type before 15 Sep.

- Minimum trading activity is probably a trade-count or turnover threshold. Exact number comes 15 Sep.

- No published rubric, no published winning reports exist anywhere. If anyone hands you a “winning report,” it didn’t come from Wharton.

## Skill gaps: where the team is starting from

- Reading an income statement, balance sheet, cash flow statement: floor, ~3 hrs. Zero, everyone.

- Discounting and time value of money: floor, ~2 hrs. Zero for most; prior IB/DCF exposure starts partway there.

- Instruments (stocks, bonds, ETFs, mutual funds, index funds): floor, ~4 hrs. Zero, everyone.

- Expense ratios and fund costs: floor, ~1.5 hrs. Zero, everyone.

- Order types, bid-ask spread, execution: floor, ~1.5 hrs. Zero, everyone.

- WInS platform mechanics and approved list: floor, ~2 hrs. Unavailable until 15 Sep.

- Portfolio theory (correlation, variance, efficient frontier): floor + Role B depth, ~3 floor / 5 depth hrs. Zero, everyone.

- CAPM, beta, systematic vs idiosyncratic risk: floor + Role B depth, ~2 floor / 4 depth hrs. Zero, everyone.

- Asset allocation: floor, ~4 hrs. Zero, everyone.

- Diversification and risk measurement: floor, ~3 hrs. Zero, everyone.

- Writing an IPS: floor + Role A depth, ~4 floor / 5 depth hrs. Zero, everyone.

- Benchmark selection and rebalancing policy: floor, ~2 hrs. Zero, everyone.

- Macro and market context: floor thin + Role A/D depth, ~2 floor / 4 depth hrs. Zero, everyone.

- Behavioural finance: floor thin + Role A depth, ~1.5 floor / 3 depth hrs. Zero, everyone.

- Trading notes discipline: floor, everyone, ~1 hr. Nobody has this yet.

- Defending an argument under questioning: floor, everyone, ~4 hrs across red-team drills. Likely weak.

- Coding & quantitative tooling: depth only, Role D (Peter, Giang), ~6 hrs learning the tools plus build time. Missing: yfinance, PyPortfolioOpt, fredapi specifically.

# Resources, area by area

## Area 0: Foundations

Everyone’s floor: which statement shows revenue, debt, cash movement; why net income and operating cash flow differ; why a future dollar is worth less. No modeling required. Depth (Role A): enough valuation vocabulary to read an analyst note, R19 if time allows. Floor: R1, R2, R3. No corporate finance course here, no DCF and no capital budgeting in this competition.

## Area 1: Market mechanics and instruments

Everyone’s floor: define, cold, stock/bond/mutual fund/ETF/index fund/expense ratio/dividend/market order/limit order/bid-ask spread. One ETF-vs-mutual-fund difference. Normal expense-ratio range. What happens when a limit order doesn’t fill. Depth (Role C): fund structure, creation/redemption, tracking error, the full WInS order screen. Floor: R5, R6, R7, R9, R10. Depth: R8, R16.

## Area 2: Portfolio theory

Everyone’s floor: state that combining assets that don’t move in lockstep lowers volatility, using the word “correlation.” What the efficient frontier is, plainly. What beta measures and the market’s own beta value. Depth (Role B):

mean-variance analysis, tangency portfolio, capital market line, systematic vs idiosyncratic risk. Depth: R14, R20, R21.

## Area 3: Asset allocation

Everyone’s floor: take a client’s horizon, liquidity needs and risk tolerance and say what allocation follows, and why. State the team’s target allocation in percentages and defend each band. Depth (Role B): how horizon changes equity weight, rebalancing rule rationale, allocation ranges vs point targets. Floor + depth: R11 (allocation and risk sections).

## Area 4: Diversification and risk

Everyone’s floor: why correlation below 1 reduces volatility, pointing to two named holdings doing that job. Diversifiable vs non-diversifiable risk. Reading a standard deviation and a max-drawdown figure. Depth (Role B): variance, covariance, correlation as quantities; why correlation rises in a crisis. Depth: R13, R15. R13’s correlation-in-a-crisis point is the best single thing the team can put in front of a judge.

## Area 5: Writing an IPS

Everyone’s floor: name the IPS sections in order. Distinguish ability to take risk from willingness, and know what to do when the two conflict. Know each client constraint and where it lives. Depth (Role A): full CFA element list, governance language, rebalancing policy, writing a measurable return objective. Depth: R11 (full). Floor: R12, R4.

## Area 6: Macro and market analysis

Everyone’s floor: name the two or three macro conditions the strategy assumes, where the data came from, and what would falsify the assumption. No forecasting. Depth, split two ways: Role D pulls the actual FRED series and builds the pipeline, Role A writes the two paragraphs of context. Overkill warning: most losing high-school reports are 40% macro commentary that drives zero decisions.

## Area 7: Behavioral finance

Everyone’s floor: name two specific biases and state the mechanism by which a written IPS protects a client from acting on them during a downturn. Depth (Role A): prospect theory, the value function’s shape, why policy documents work as commitment devices. Depth: R17.

## Area 8: Coding and quantitative tooling

Not everyone’s floor. Depth (Role D, Peter and Giang): pulling clean historical price data, computing a real correlation matrix and efficient frontier on the team’s actual candidate list, backtesting basic risk metrics against a benchmark, automating the FRED macro pulls Role A needs. Depth: R23, R24, R25, R26, R27. Explicitly out of scope: DCF, comps, LBO, or any company-level valuation modelling, because Wharton doesn’t grade a valuation.

## Overkill: don’t spend time on these

- DCF modeling. Wharton wants a portfolio strategy, not a company valuation. No requirement mentions it.

- Options, futures, derivatives. Cut 15.401 Sessions 9–12, ~5 hours. Almost certainly outside the approved securities list anyway.

- Technical analysis / chart patterns / momentum systems. Wharton says performance barely matters.

- Watching a full semester lecture course as a group. All 23 Shiller lectures = 143 person-hours for maybe 8 hours of usable material. Assign 5 lectures to individual owners.

- 15.401 in full. 27 hours solo. Take Sessions 13–16 (~5.3 hrs), optionally 2–4. Skip the rest.

- Macro forecasting. Nobody can do it and judges know it. Two paragraphs, tied to a decision.

- CFA Level I curriculum. Out of scope, and paid materials raise a rules question nobody needs.

- Any paid course or coaching. Explicitly prohibited. Disqualification risk.

- Optimizing portfolio performance. The single biggest time-waster in October. Wharton says it doesn’t decide the outcome.

PART 2: THE SCHEDULE

## Ground rules

- 43 sessions × 2 hours across 15 weeks, 3 sessions/week (Sessions 1 and 2 already done) = 86 hours per person. Programmed work is about 78 hours. Don’t fill the buffer.

- SHARED = everyone does the same thing together. SPLIT = owners work different material in parallel, then teach it back.

- Watch for reduced weeks: Vietnam National Day (2 Sep) shrinks Week 2, Vietnamese Teachers’ Day (20 Nov) may shrink Week 13, Session 10 is general buffer, US Thanksgiving means Week 14 has a buffer session too.

- Before the first trade, the team needs: instrument definitions, order types, bid-ask spread, approved-securities constraint, trading-note format. That’s all of Block A.

- Better learned live, not front-loaded: rebalancing, the gap between intended and executed allocation, how correlation behaves in a real held portfolio, defending a losing position.

- Tin Tin, added to the team at the Session 3–4 stage, joins the plan from wherever the team currently sits. No separate catch-up track, the team is still early in Block A.

## BLOCK A: Pre-trading foundation (22 Aug – 27 Sep 2026, Sessions 3–16, 28 hours)

### Week 1 (22–28 Aug)

- Session 3 (SHARED): Instruments floor pt.1. Do: R6 full, R2 intro. Produce: shared glossary sheet, 20 terms.

### Week 2 (29 Aug–4 Sep)

- Session 4 (SHARED): Fees, expense ratios, index funds. Do: R7. Produce: expense-ratio table for five real ETFs with 20-year cost difference on $500,000.

- Session 5 (SHARED): Order types, bid-ask, execution. Do: R5. Produce: trade-ticket template.

- Session 6 (SHARED): Discounting and time value. Do: R1. Produce: one-page explanation of why a dollar in five years is worth less.

### Week 3 (5–11 Sep)

- Session 7 (SHARED): Role assignment and first teach-back drill. Do: Part 3 role menu; Session 3–6 material. Produce: Role A is pre-assigned as Tin Tin plus one TBD co-owner, the co-owner decision made during this session. The remaining two of Bao, Valt, and Long are assigned Role B and Role C during this same session. Role D remains pre-locked to Peter and Giang. Each person teaches one Block A concept back for 10 minutes.

- Session 8 (SHARED): IPS anatomy. Do: R11 scope/purpose/governance. Produce: blank IPS skeleton.

- Session 9 (SHARED): REGISTRATION CHECKPOINT; risk tolerance; ethics. Do: R4 registration steps, R12 skim, R11 risk tolerance section. Produce: written confirmation advisor has registered and WInS accounts exist.

Ability-vs-willingness one-pager.

### Week 4 (12–18 Sep)

- Session 10 (BUFFER): Reserved. Protect it.

- Session 11 (SHARED): CASE STUDY INTAKE. Do: actual competition materials released 15 Sep. Produce: delta memo, what changes in this plan.

- Session 12 (SHARED): WInS platform mechanics. Do: R10. Produce: five practice trades, each with a completed trade ticket.

### Week 5 (19–25 Sep)

- Session 13 (SPLIT): Depth round 1 pt.1. Do: Role B: R14, R13. Role A: R11 core, R19 optional. Role C: R8. Role D Peter: environment setup, R23, pull historical prices. Role D Giang: R24, review pulled data. Produce: notes only.

- Session 14 (SPLIT): Depth round 1 pt.2 + brief writing. Do: Role B: R20. Role D Peter & Giang together: R25, build a correlation matrix and first efficient-frontier plot. Produce: five one-page briefs, each claim carrying a source pointer.

- Session 15 (SHARED): Second-reader checks and teach-back round 1. Produce: five verified briefs, five comprehension checks.

### Week 6 (26 Sep–2 Oct)

- Session 16 (SHARED): Client objectives and constraints. Do: case study, R11 objectives/constraints. Produce: objectives-and-constraints table, draft target allocation.

BLOCK B: Active trading + IPS drafting (28 Sep – 6 Nov 2026, Sessions 17–33, 34 hours)

### Week 6 (26 Sep–2 Oct)

- Session 17 (SHARED): First trades. Produce: initial portfolio built, one trading note per position.

- Session 18 (SHARED): Benchmark and rebalancing policy. Do: R11 risk management/rebalancing. Produce: benchmark named and defended, rebalancing rule stated as a trigger.

### Week 7 (3–9 Oct)

- ROSTER DEADLINE THIS WEEK: Friday 9 Oct. Submit official team roster and team name via SurveyMonkey Apply before Session 19 ends.

- Session 19 (SHARED): Trading notes audit. Produce: every position has a note naming the reason, the client objective, and what would make you sell. Confirmation roster and team name submitted.

- Session 20 (SPLIT): Depth round 2 pt.1. Do: Role B: R21, R15. Role A: R17 core, R18 optional. Role C: R9. Role D Peter: benchmark-tracking / rebalancing-drift dashboard on real WInS data. Role D Giang: R26 + R27, pull three real macro series for Role A. Produce: notes and draft briefs.

- Session 21 (SHARED): Teach-back round 2 plus second-reader checks.

### Week 8 (10–16 Oct)

- Session 22 (SHARED): IPS drafting: scope, purpose, governance, client profile. Do: R11 scope/governance. Produce: IPS sections 1–2.

- Session 23 (SHARED): IPS drafting: return and risk objectives. Do: R11 objectives, Role B’s Session 15 brief. Produce: IPS section 3.

- Session 24 (SPLIT, Owners): Owner sections plus second-reader passes. Role D drafts the quantitative-evidence exhibits (correlation matrix, efficient-frontier chart) that Role A and Role B write around. For each exhibit, Role D also writes a short technical note, three to four sentences in plain language: the method used, the assumptions it rests on, what the number or chart shows, and one caveat. Role A pulls from this note instead of interpreting the exhibit cold.

### Week 9 (17–23 Oct)

- Session 25 (SHARED): IPS drafting: constraints. Do: R11 constraints. Produce: IPS section 4.

- Session 26 (SHARED): Allocation rationale and correlation evidence. Do: Role B’s brief, Role D’s correlation output, live WInS data. Produce: written rationale naming two holdings doing the diversification job.

- Session 27 (SHARED): Portfolio review against draft IPS. Produce: any position that contradicts the IPS is closed, or the IPS is corrected. Trading notes updated. Also a drift-test check on the shared floor from Block A.

### Week 10 (24–30 Oct)

- Session 28 (SHARED): Full IPS assembly. Produce: complete IPS draft, single document, consistent voice.

- Session 29 (SHARED): External fact check. Do: the audit prompt in Part 3, advisor review. Produce: audit output logged, every flagged claim fixed or defended.

- Session 30 (SHARED): Revision. Produce: revised IPS. Checkpoint beforehand: Role D signs off on the final wording of any sentence describing their exhibits, five minutes per exhibit, not a rewrite.

### Week 11 (31 Oct–6 Nov)

- Session 31 (SHARED): Red team. Produce: each person defends a section they did not write, cold, no notes.

- Session 32 (SHARED): Final edits, citations, AI disclosure.

- Session 33 (SHARED): SUBMIT IPS. Do this on 4 or 5 Nov local time, not on the deadline.

## BLOCK C: IPS to final report (7 Nov – 4 Dec 2026, Sessions 34–45, 24 hours)

### Week 12 (7–13 Nov)

- Session 34 (SHARED): Final report structure. Produce: outline with a named owner and word budget per section.

- Session 35–36 (SPLIT, Owners): Section drafting rounds 1. Role D: refined exhibits, not a prose section.

### Week 13 (14–20 Nov)

- Session 37 (SHARED): Performance attribution against benchmark. Do: WInS portfolio history, benchmark data, Role D’s dashboard. Produce: table of portfolio vs benchmark with a written explanation.

- Session 38 (SPLIT, Owners): Section drafting round 2.

- Session 39 (SHARED): Assemble draft 1, second-reader swap.

### Week 14 (21–27 Nov)

- Session 40 (SHARED): Revision pass. Do: checker comments. Produce: draft 2. Also the drift-test re-check on Block A depth material. Checkpoint beforehand: Role D signs off on the final wording of any sentence describing their exhibits, five minutes per exhibit, not a rewrite.

- Session 41 (SHARED): External fact check.

- Session 42 (BUFFER): Reserved. US markets closed 26 Nov, half day 27 Nov.

### Week 15 (28 Nov–4 Dec)

- Session 43 (SHARED): Red team and semifinal drill. Produce: every person answers three questions on a section they did not write, cold.

- Session 44 (SHARED): Final edits and citations.

- Session 45 (SHARED): SUBMIT. Do this on 2 or 3 Dec local time.

## Not yet scheduled: semifinal and finals prep window

Flag for a future session: no calendar hours are booked anywhere between the 4 Dec Final Report submission and the 29–30 Apr Global Finale. Presentation and narrative work has a named owner now, Tin Tin via Role A, but the Jan–Apr semifinal and finals prep window still needs its own scheduling pass. This change list assigns ownership, not hours; treat the gap as open.

## Coverage check: nothing gets orphaned

| ID | Sessions | Hrs | Owner / notes |
| --- | --- | --- | --- |
| R4 | 1, 2, 9, 19 | 4 shared | Floor |
| R11 | 8, 9, 13, 16, 18, 22, 23, 25 | 3 depth, 6shared | Floor + Depth, Role A |
| R14 / R13 | 13 | 1.5 each | Depth, Role B |
| R20 / R21 | 14 / 20 | 2.7 each | Depth, Role B |
| R8 | 13, 14 | 2.5 | Depth, Role C |
| R9 | 20 | 1 | Floor tool, now also feeds Role C’s live risk-monitoring check |
| R17 | 20 | 1.5 | Depth, Role A |
| R22 | 20 | 1.5 | Pipeline: Role D. Interpretation: Role A |
| R23 | 13 | 1 | Depth, Role D (Peter lead) |
| R24 | 13 | 0.75 | Depth, Role D (Giang lead) |
| R25 | 14, 20 | 3 | Depth, Role D (joint). Verification step now includes a rotating second checker outside Role D confirming the notebookoutput before any figure goes into the IPS or report. |
| R26 / R27 | 20 | 1 / ~0.1 | Depth, Role D (Giang lead) |

Everything with an “optional, cut if short” tag has a stated reason next to it. Everything else is scheduled somewhere.

PART 3: WHO OWNS WHAT

Written so anyone on the team can pick up a role cold and run with it. This part carries the changes agreed on across planning passes:

- Role B / Role C overlap fixed

- Role A now held jointly by two people (Tin Tin plus a co-owner) instead of split three ways across Bao, Valt, and Long

- A hard scope cap added to Role D

- A fixed Session 7 role menu

- The single-points-of-failure, teach-back, and verification sections updated to match

# The four role tracks

## Role A: IPS, Client & Editorial Owner (Tin Tin + co-owner)

- Owns: the IPS document (client profile, objectives, constraints, governance language) and the final report’s structure, voice, and citations, split across two co-owners:

  - Tin Tin leads the writing and voice across both graded documents, and owns the narrative arc and presentation prep for semifinals, starting in October.

  - The co-owner handles structure, citation formatting, and deadline tracking, and is first-pass editor on Tin Tin’s drafts before either document reaches Role B, the formal second reader.

- This is the highest-workload, highest-stakes role on the team, holding both graded documents.

  - Held jointly by two people because the writing/voice work and the structure/citation work are different skills, not because the team’s headcount forces a split.

  - Headcount math: Role D is locked to Peter and Giang, Tin Tin leads Role A, leaving exactly two people from Bao, Valt, and Long for the Role A co-owner seat plus Role B and Role C.

  - Role A still produces one unified brief per topic during the teach-back protocol, not two separate briefs. The point of the two-person structure is one shared voice.

- Selection at Session 7 is made on stated criteria, not on who volunteers first. Tin Tin is pre-assigned as lead. The co-owner seat goes to whichever of Bao, Valt, or Long is most reliable under deadlines, not whoever is most enthusiastic.

- Automatic backup trigger:

  - If Tin Tin misses two sessions in a row, or misses a milestone deliverable date, the co-owner absorbs voice and writing duties. Some quality drift is acceptable short term, and Role B remains available as a further backup.

  - If the co-owner goes dark instead, Tin Tin absorbs the structural and citation work solo. This is the smaller half of the job and workable on its own.

- Citation formatting and the AI-disclosure log (Sessions 32, 44) sit with the Role A co-owner as part of the structure/citation ownership above, not spread out to Role B or C.

- Goes deep on: writing an IPS, behavioral finance, macro context jointly with Role D (Role D pulls and structures the FRED data, Role A writes the interpretation).

- Resources: R11 (full), R17, R18 (optional), R19 (optional).

## Role B: Portfolio & Risk Owner

- Owns: target allocation and weights, the written risk policy, rebalancing rule design (the trigger, not the execution), benchmark selection and its written justification, the risk section and diversification evidence.

- What moved to Role C: live monitoring of trades against the written risk policy, pulling the actual benchmark comparison numbers each session, and executing a rebalancing trade once B’s trigger fires. Role B designs the logic, Role C runs it against real positions. This removes the overlap where both roles were touching risk and rebalancing at once.

- Goes deep on: portfolio theory, asset allocation, diversification and risk.

- Resources: R13, R14, R15, R20, R21.

- Why it matters: every “why did you choose this” and “how risky is this” question from a judge lands here. Works directly off Role D’s correlation matrix and efficient-frontier output instead of computing it by hand. Fixed backup for Role A.

## Role C: Instruments & Trading Owner

- Owns: the WInS account, every trade, the trading-notes deliverable, the approved-securities list.

- Added from Role B: checking every live trade against Role B’s written risk policy as it happens (if a position gets too concentrated or breaks a stated bound, C catches it in real time, not B reviewing it after the fact), pulling the live benchmark comparison numbers each session, and executing a rebalancing trade when B’s trigger fires, logged in the trading notes. This is C doing more of what C already does (it already owns the Session 27 portfolio-vs-IPS check and the live trade log), not a new skill.

- Goes deep on: market mechanics and instruments.

- Resources: R8, R9, R16 (optional).

- Why it matters: trading notes are graded and the only deliverable that can’t be reconstructed later. Best fit: the most consistent person on the team, the one who does the same unglamorous thing every session without fail.

## Role D: Coding & Quantitative Modelling Owner (Peter and Giang)

- Owns: the correlation matrix and efficient-frontier calculation (feeds Role B), the benchmark-tracking and rebalancing-drift dashboards (feeds Role B and C), the automated FRED data pipeline (feeds Role A), the shared trading-notes log system (feeds Role C).

- The split: Peter leads the build (scripts, data pipeline, dashboard). Giang leads the modelling and interpretation (mean-variance optimization, correlation output, translating backtested drawdown and volatility into the language Role B needs). Roughly 40% Peter / 60% Giang on work that’s specifically financial-modelling rather than pure infrastructure. Neither of you owns a silo the other can’t step into.

- Scope cap: every exhibit Role D produces has to map to one specific claim already identified in the IPS or report that Role A or Role B will actually use. No exploratory runs, no extra strategies backtested beyond the team’s actual candidate list, nothing built because it’s possible. If a new modelling idea comes up mid-competition, it goes to Role B first as a question, would this claim actually appear in the document, before it goes into the build queue.

- Verification: a second person outside Role D, rotating, reruns the notebook and confirms the same output before any figure goes into the IPS or report. This sits on top of Role C’s existing source-pointer check, which confirms a claim matches its source but doesn’t independently verify the math.

- Explicitly does not do: DCF or company-level valuation modelling. The case has no valuation requirement, Wharton grades a portfolio strategy, not a stock pick. “Financial modelling” here means portfolio-level quantitative modelling, not corporate finance modelling. DCF practice as a personal project is fine, just keep it outside the team’s 86-hour budget, it produces nothing gradable.

- Goes deep on: R23, R24, R25, R26.

- Why it matters: the one role with built-in redundancy, if either of you goes dark the other already knows the material and can absorb it solo. Most likely to produce the evidence that separates your report from a typical beginner team’s: an actual computed efficient frontier with your real holdings on it, not just a paragraph asserting diversification works.

## Where the judging weight actually sits

- Role A owns alignment and clarity, the highest-workload, highest-stakes role, protected by the automatic backup trigger above.

- Role B owns strategy quality and a good chunk of research depth, and is Role A’s live backup.

- Role C is load-bearing but mechanical, now also the team’s real-time risk and rebalancing check, a solid fit for whoever is most reliable at doing the same thing every session.

- Role D produces the research depth that’s hardest for a beginner team to fake, real computed evidence instead of assertions, scoped tightly so it stays evidence and doesn’t become a side project.

## Session 7 role menu: read this at role assignment

Fixed menu. Tin Tin is pre-assigned as Role A lead, joining from Session 3 onward. Bao, Valt and Long pick from these three seats as written, they don’t redesign them in the room: one becomes Tin Tin’s Role A co-owner, the other two take Role B and Role C.

#### Role A co-owner (with Tin Tin)

Owns: Structure, citation formatting, deadline tracking, and first-pass editor on Tin Tin’s drafts before either document reaches Role B, the formal second reader.

Best fit: Reliable under deadlines, not necessarily the fastest writer, that’s Tin Tin’s job.

Backup: if the co-owner goes dark, Tin Tin absorbs the structural and citation work solo, the smaller half of the job. If Tin Tin goes dark, the co-owner absorbs voice and writing duties, with Role B as further backup.

#### Role B: Portfolio and Risk Owner

Owns: Owns allocation, the written risk policy, rebalancing rule design, benchmark selection and its written justification. Best fit: Reasons well with numbers and can also write cleanly, since they’re A’s backup.

Backup: Role A, via the same fixed second-reader pairing.

#### Role C: Instruments and Trading Owner

Owns: Owns the WInS account, every trade, trading notes, the approved-securities list, live risk monitoring against B’s policy, rebalancing execution, benchmark data tracking.

Best fit: The most consistent person on the team, does the same unglamorous thing every session without fail. Backup: Role D is the fastest secondary pickup if needed, they built the trading-notes tooling.

# The shared floor: every single one of you, cold, no notes

Any team member can be questioned on any part at semifinals. This is the actual bar. None of these are “understands diversification.” Each is a specific sentence with a specific object in it. If someone can’t produce it in ten seconds, they don’t have the floor yet.

- Foundations: which statement holds revenue/debt/cash movement; why net income and operating cash flow differ (one specific reason); why a future dollar is worth less than today’s.

- Market mechanics: definitions of stock, bond, ETF, mutual fund, index fund, expense ratio, dividend, market order, limit order, bid-ask spread. One ETF-vs-mutual-fund structural difference. The expense ratio of every fund the team holds, to two decimals, and what it costs the client per year on the actual position size.

- Portfolio theory: why correlation below 1 lowers portfolio volatility. What beta measures, and the market’s own beta. The efficient frontier, in one sentence.

- Asset allocation: the team’s target allocation in percentages, with a one-sentence defense per band tied to a specific client fact. The gap between policy and current allocation, and why it exists.

- Diversification and risk: two named holdings doing the diversification job, with evidence. Diversifiable vs non-diversifiable risk. The portfolio’s largest drawdown and its cause.

- Writing an IPS: the IPS sections, in order. Ability vs willingness to take risk, and what the team did when they conflicted. Each client constraint and where it lives in the document.

- Macro: the two or three macro assumptions behind the strategy, and where each number came from.

- Behavioral finance: two named biases and the mechanism by which the IPS protects the client from them.

- Where the numbers came from: at a high level, how the correlation, volatility, and efficient-frontier figures were actually produced. Historical price data pulled and run through a Python tool. You don’t need to write the code, just not freeze on the question.

This floor is re-tested twice, not just taught once: a drift-check runs in Session 27 alongside the IPS-vs-portfolio review, and again in Session 40 alongside the report revision pass, so floor recall gets the same spaced re-test that the SPLIT depth briefs already get.

# Single points of failure

| Who / what | What’s lost | Backup |
| --- | --- | --- |
| Advisor | Registration and submission access,cannot register or submit without them | Identify a second willing teacher in August.Don’t wait until you need one. |
| Team leader (Peter) | Submission access; leader can’t bechanged after 28 Sep without written approval | Choose a leader who is reliable. A secondperson holds the SurveyMonkey Apply login. |
| Role A, Tin Tin | The IPS and report’s writing, voice, and narrative arc, the single highest-impact failure on the team if unaddressed | The co-owner absorbs voice and writing duties. Some quality drift is acceptable short term. Role B remains available as a further backup, per the existing escalation pattern. |
| Role A, co-owner | Structure, citation formatting, and deadline tracking on both graded documents | Tin Tin absorbs the structural and citation side solo. This is the smaller half of the job and is workable. |
| Role B | The allocation rationale and therisk/benchmarkevidence | Role A absorbs it, both have readeverything through the second-reader pairing. |
| Role C | Trading notes and WInS access | Fatal if credentials sit with one person. All six have WInS login from day one, notes live in the shared doc. Role D is fastest secondary pickup. |
| Role D, Peter | The build side of the tooling | Giang absorbs it, real built-in redundancy. |
| Role D, Giang | The modelling and interpretation side | Peter absorbs it, same logic. |
| Both Peter and Giang | Unlikely, but the full quant workstream | Fallback is Role C. Exhibits simplify to what can be computed by hand or in a spreadsheet, the shared floor already covers what those need to say. |

- Every backup pairing above is also the second-reader pairing, on purpose. Your checker is your backup, because they already know your material.

- Drop below four members and the team is disqualified, at any point, not just at the start. With six, there’s exactly two spares. Removing anyone needs written advisor approval. Adding anyone is only possible before the 9 Oct roster submission, though the team is already at Wharton’s six-person ceiling, so no further additions are possible regardless of timing.

- If anyone’s wavering, sort it out before Session 19’s week, not after.

# Teach-back protocol

| Step | Time | What happens |
| --- | --- | --- |
| 1. Written brief | 45 min, inside the SPLITsession | One page: what this covers (2 sentences), 5–8 claims one per line, what it changes about the strategy (2 sentences), what’s still unclear(1 line). Every claim carries a source pointer (lecture+timestamp, page, resource ID, or section heading). No pointer, the claim gets struck before anyone reads it. |
| 2. Second-reader check | 30 min, before the groupsees the brief | Fixed pairings for the whole competition: Role A  Role B, Role C  Role D. Role C checks both of Role D’s briefs. Peter and Giangcheck each other’s briefs first. Tin Tin and the Role A co-owner check each other’s material first too, before Role B sees either one, the same pattern. Checker opens the source at the pointer and marks each claim confirmed / misstated / not found. |
| 3. Verbal walkthrough | 15 min per owner, start of aSHARED session | The other four have the brief in hand. Five people × 15 min = 75 min (Role A’s two co-owners produce one joint brief together, not two; Role D still produces two separate briefs; headcount stays five). |
| 4. Comprehension check | 10 min, same session | Question pulled from the source material, not written by the owner.See Mechanism 1 below. |

Writing first isn’t a formality. Talking lets you skate past what you didn’t understand. Writing doesn’t. This is why Sessions 15 and 21 are entirely teach-back with no new material.

# Verification: how the team catches its own mistakes

The specific failure this is designed against: someone misunderstands a concept, teaches it confidently, then writes a comprehension check that tests their own misunderstanding, and the whole team walks into semifinals believing the same wrong thing.

## Mechanism 1: checks come from the source, never from the owner

The per-resource question bank (one check per R-number: R14, R13, R15, R17, R20, R21, R11, R8, R5, R22, R23/R24, R25) is no longer pre-written into this plan. It’s quiz content, not planning content, and nobody reads a wall of quiz questions while scheduling sessions. Generate the check live at Step 4 of the teach-back protocol, pulled from that resource’s own source material, never from the owner’s memory. Keep it in a separate working file if you want a bank to draw from.

## Mechanism 2: triage

- Load-bearing = drives an allocation call, a risk assessment, a benchmark choice, or a client-objective mapping, or ends up as a number in the IPS/report. These get a source pointer, a second-reader check, and an external audit.

- Incidental = definitions, history, color. Source pointer and second-reader only.

- Roughly 20% of claims are load-bearing, put 60% of verification effort there.

## Mechanism 3: external fact check

- Run the IPS and final report through an audit at Sessions 29 and 41, plus any brief where the second reader flagged two or more claims.

- Wharton allows AI for brainstorming, bans submitting AI work as your own, and requires citation of anything AI-assisted. Checking your own writing against your own sources isn’t AI-generated content and doesn’t need citation, using it to write a section does. Keep a log.

- Also send the same brief to the advisor for the same check.

#### Reusable audit prompt, paste this with a brief attached:

You are auditing a student-written brief against its cited sources. Every claim carries a source pointer in square brackets. For each claim: (1) is the pointer specific enough to check, lecture+timestamp, page, resource ID, or named section? Flag if not. (2) Is the claim consistent with what that source actually says? If you don’t know the source well enough to judge, say so rather than guessing. (3) Is it load-bearing (would change an allocation call, risk assessment, or client-objective mapping) or incidental? Then list separately: any claim that’s wrong; any claim that’s technically true but would collapse under an expert’s follow-up question; any load-bearing claim with no source pointer at all. Don’t rewrite the brief, don’t add content, don’t soften the assessment. If something’s wrong, say it’s wrong.

## How a failed teach-back actually looks: catch it in week 3, not at semifinals

- The vocabulary echo: repeats the owner’s exact phrasing but can’t rephrase it. Memorized a sentence, didn’t learn the thing.

- The frozen follow-up: first answer’s fine, the second question (“so what would happen if that weren’t true?”) kills them.

- Silence during the walkthrough: zero questions from four beginners hearing new material means either nobody’s following or nobody read the brief. Redo it.

- The owner can’t answer about their own module: the dangerous one, the misunderstanding is at the source. Escalate straight to the external check.

- The drift test: two weeks after a teach-back, ask the comprehension-check question again, cold. Under 50% team-wide retention means the transfer didn’t happen, rebuild the module. Scheduled at Sessions 27 and 40.